## Sprint
|  |  |  | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week) | [6 empty] | Week #3 (10 hrs / week) | [6 empty] | Week #4 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 50 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28
|  |  |  | 2014-09-13 | 2014-09-14 | 2014-09-15 | 2014-09-16 | 2014-09-17 | 2014-09-18 | 2014-09-19 | 2014-09-20 | 2014-09-21 | 2014-09-22 | 2014-09-23 | 2014-09-24 | 2014-09-25 | 2014-09-26 | 2014-09-27 | 2014-09-28 | 2014-09-29 | 2014-09-30 | 2014-10-01 | 2014-10-02 | 2014-10-03 | 2014-10-04 | 2014-10-05 | 2014-10-06 | 2014-10-07 | 2014-10-08 | 2014-10-09 | 2014-10-10
|  |  |  | 200 | 191 | 182 | 173 | 164 | 155 | 146 | 137 | 128 | 119 | 110 | 101 | 92 | 83 | 74 | 65 | 56 | 47 | 38 | 29 | 20 | 11 | 2 | -7 | -16 | -25 | -34 | 0 | Ideal Burndown
|  |  | 200 | 2014-09-13: 10; 2014-09-14: 10; 2014-09-15: 7; 2014-09-16: 6; 2014-09-17: 4; 2014-09-18: 4; 2014-09-19: 4; 2014-09-20: 4; 2014-09-21: 4; 2014-09-22: 4; 2014-09-23: 4 | Remaining Hrs (Total)
[Spike] Project Planning | Project Search and Environment Setup - 1 | Shreyas | 3 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Project Search and Environment Setup - 2 | Brinda
| Project Search and Environment Setup - 3 | Arpitha
| Project Search and Environment Setup - 4 | Sagar
| Project Search and Environment Setup - 5 | Sai
| Requirement Analysis and backlog planning | Shreyas | 7 | 7 | 7 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Feature Planning - 1 | Brinda
| Feature Planning - 2 | Arpitha
| Documentation Analysis | Sagar
| Team Coordination and Follow-up | Sai
Code Design and Analysis | Code Design and Analysis for adding functionality - Reverse words | Shreyas | 5 | 2014-09-13: 5; 2014-09-14: 5; 2014-09-15: 5; 2014-09-16: 5; 2014-09-17: 5; 2014-09-18: 5; 2014-09-19: 5; 2014-09-20: 5; 2014-09-21: 5
| Code Design and Analysis for adding | Brinda
| Code Design and Analysis for adding | Arpitha
| Code Design and Analysis for adding | Sagar
| Code Design and Analysis for adding | Sai
Code Design and Analysis | Feature Implementation for adding functionality - Reverse words | Shreyas | 15 | 2014-09-13: 15; 2014-09-14: 15; 2014-09-15: 15; 2014-09-16: 15; 2014-09-17: 15; 2014-09-18: 15; 2014-09-19: 15; 2014-09-20: 15; 2014-09-21: 15; 2014-09-22: 15; 2014-09-23: 15; 2014-09-24: 15; 2014-09-25: 15
| Feature Implementation for adding | Brinda
| Feature Implementation for adding | Arpitha
| Feature Implementation for adding | Sagar
| Feature Implementation for adding | Sai
Feature Testing | Testing for | Shreyas
| Testing for | Brinda
| Testing for | Arpitha
| Testing for | Sagar
| Testing for | Sai
Code Refactoring and Documentation |  | Shreyas
Brinda
Arpitha
Sagar
Sai
Shreyas Kulkarni | 10 hours / Week
Brinda | 10 hours / Week
Sai Swarup | 10 hours / Week
Arpitha | 10 hours / Week
Sagar | 10 hours / Week
Total Available Hours During Sprint: | 200