## Sprint
|  |  |  | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week) | [6 empty] | Week #3 (10 hrs / week) | [6 empty] | Week #4 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 50 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28
|  |  |  | 2014-11-01 | 2014-11-02 | 2014-11-03 | 2014-11-04 | 2014-11-05 | 2014-11-06 | 2014-11-07 | 2014-11-08 | 2014-11-09 | 2014-11-10 | 2014-11-11 | 2014-11-12 | 2014-11-13 | 2014-11-14 | 2014-11-15 | 2014-11-16 | 2014-11-17 | 2014-11-18 | 2014-11-19 | 2014-11-20 | 2014-11-21 | 2014-11-22 | 2014-11-23 | 2014-11-24 | 2014-11-25 | 2014-11-26 | 2014-11-27 | 2014-11-28
|  |  | 200 | 193 | 186 | 179 | 172 | 165 | 158 | 151 | 144 | 137 | 130 | 123 | 116 | 109 | 102 | 95 | 88 | 81 | 74 | 67 | 60 | 53 | 46 | 39 | 32 | 25 | 18 | 11 | 4 | Ideal Burndown
|  |  | 200 | 168 | 163 | 155 | 146 | 131 | 124 | 118 | 114 | 111 | 103 | 99 | 90 | 84 | 67 | 48 | 44 | 38 | 27 | 24 | 22 | 21 | 12 | 10 | 7 | 4 | 1 | 0 | 0 | Remaining Hrs (Total)
[Spike] Project Planning | Project Search and Environment Setup - 1 | Shreyas | 3 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Project Search and Environment Setup - 2 | Brinda | 4 | 4 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Project Search and Environment Setup - 3 | Arpitha | 4 | 4 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Project Search and Environment Setup - 4 | Sagar | 3 | 3 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Project Search and Environment Setup - 5 | Sai | 3 | 3 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Requirement Analysis and backlog planning | Shreyas | 7 | 7 | 7 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Feature Planning - 1 | Brinda | 6 | 6 | 6 | 6 | 6 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Feature Planning - 2 | Arpitha | 7 | 7 | 6 | 6 | 5 | 4 | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Documentation Analysis | Sagar | 7 | 7 | 7 | 7 | 6 | 5 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Team Coordination and Follow-up | Sai | 7 | 7 | 6 | 7 | 7 | 3 | 4 | 4 | 3 | 2 | 2 | 2 | 2 | 2 | 3 | 2 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Code Design and Analysis | Code Design and Analysis for adding functionality - Reverse words | Shreyas | 5 | 2014-11-01: 5; 2014-11-02: 5; 2014-11-03: 5; 2014-11-04: 5; 2014-11-05: 5; 2014-11-06: 5; 2014-11-07: 5; 2014-11-08: 5; 2014-11-09: 5
| Code Design and Analysis for adding functionality - Booster points Meteor and Learn Git | Brinda | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Code Design and Analysis for adding functionality- Play and Pause Button | Arpitha | 7 | 7 | 6 | 6 | 6 | 5 | 5 | 4 | 4 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Code Design and Analysis for adding | Sagar | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Code Design and Analysis for adding | Sai | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 5 | 5 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Code Design and Analysis | Feature Implementation for adding functionality - Reverse words | Shreyas | 15 | 2014-11-01: 15; 2014-11-02: 15; 2014-11-03: 15; 2014-11-04: 15; 2014-11-05: 15; 2014-11-06: 15; 2014-11-07: 15; 2014-11-08: 15; 2014-11-09: 15; 2014-11-10: 15; 2014-11-11: 15; 2014-11-12: 15; 2014-11-13: 15
| Feature Implementation for adding functionality - Booster points Meteor | Brinda | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 11 | 11 | 8 | 6 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Feature Implementation for adding functionality- Play and Pause Button | Arpitha | 13 | 13 | 12 | 8 | 7 | 6 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Feature Implementation for adding | Sagar | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 10 | 8 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Feature Implementation for adding | Sai | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 11 | 11 | 13 | 10 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Feature Testing | Testing for | Shreyas
| Testing for functionality - Booster points Meteor and review features - Reverse Words, Masked Words, Pause Play buttons | Brinda | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Testing for functionality- Play and Pause Button | Arpitha | 3
| Testing for functionality - Masked words | Sagar | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0
| Testing for | Sai | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Code Refactoring and Documentation |  | Shreyas
| Github Administration - manage branches of peers and Architecture diagram, User Story Video and Demo Video | Brinda | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 5 | 4 | 2 | 0 | 0 | 0
| Documentation and Architecture | Arpitha | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 3 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Sagar
Sai
Shreyas Kulkarni | 10 hours / Week
Brinda | 10 hours / Week
Sai Swarup | 10 hours / Week
Arpitha | 10 hours / Week
Sagar | 10 hours / Week
Total Available Hours During Sprint: | 200